## Sheet1
WBS Code | Item Description | Estimated Time Duration (Work days)
Project Milestones
Project Starts
Design Kick-off Meeting
Design Completed
Foundation Completed
Building Enclosed
Final Inspection & Approval
Substantial Completion C of O
Flush Building
Project Ends
010 | Project Management
| Develop Work Plan | 6
| Form Project Team | 6
| Building Permits | 30
| Move In, Erect Fence, Erosion Control | 6
| Procure Contractor's Bids | 90
| Handover | 7
| Punch List & Move | 14
010 | Design
| Structural Design | 40
| Storm-Water Design | 8
| Sanitary Sewer Design | 8
| Architectural Design | 60
| On-Site Utilities Design | 8
| Mechanical Systems Design | 10
| Electrical Systems Design | 21
020 | SiteWork & Excavation
| Backfill/Restore Grade | 1
| Excavate Bsmt/Prep for Found Footings | 8
| Install Sewer Line | 15
| Backfill Int. Fnd. Walls & U/G Duct | 3
| Install Water Line/Tap | 15
| Excavate for U/G Plumbing | 2
| Backfill/Rgh Grade Foundation & Site | 3
| Prep Site for Steel | 6
| Backfill/Prep Landing | 5
| Final Paving | 1
| Landscaping & Brick Paving | 20
030 | Concrete (incl formwork, reinforced steel)
| Form/Place/Strip Balance of Footings | 6
| Form/Place/Strip Basement Walls | 12
| Prep/Place Basement Slab On Grade | 4
| Prep/Place Main Slab on Grade | 5
| Prep/pour First Floor Slab On Deck | 5
| Prep/Pour Second Floor Slab On Deck | 5
| Form/place Stair Landing Basement | 5
| Site Concrete- all Sides | 12
| Place Exterior West Slab | 3
034 | Precast Concrete
| Fab & Del Precast | 25
| Precast - Entrance | 10
040 | Masonry
| Fab & Del Brick | 55
| Install 1st & 2nd Floor Brick & Precast East | 27
| Install Gable-End Brick & Precast - East (Br dne) | 9
| Install Gable-End Brick & Precast - West | 17
| Install 1st & 2nd Floor Brick & Precast West | 15
| Install 1st & 2nd Floor Brick & Precast - North | 17
| Install 1st & 2nd Floor Brick & Precast - South | 8
050 | Metals
| Fab & Del Deck | 2
| Fabricate & Deliver Steel | 42
| Survey Anchor Bolts | 2
| Erect Steel Frame | 16
| Erect Roof Steel | 10
| Install Deck/Studs | 2
| Install Roof & Attic Decking | 9
| Install Precast Supports / Adjust | 9
| Fab & Del Stairs 1 & 2 MAIN STAIRS | 38
| fab & Del Basement Stair | 25
| Install Stairs - basement | 18
| Install Stairs Building | 30
| Fab, Del & Install Ladder & Handrail-- Attic | 15
| Install Stair Rails | 32
060 | Carpentry
| Fab & Del Millwork | 60
| Install Millwork | 10
| Install Wood Paneling | 10
| Install Plywood - Attic | 5
070 | Roof & Moisture Protection
| Fab & Del Slate Roofing | 30
| Fab & Del EPDM Roofing | 40
| Fab & Del Slate Infills North | 124
| Dampproof & Insulate Foundation | 6
| Install Roof Sheathing | 15
| Install Slate Shingles | 12
| Install EPDM - Pit & Balcony | 5
| Terminate Roofing Entrance | 2
| Install Slate Infills | 8
080 | Doors & Windows
| Fab & Del Drs/Frames/Hardware | 15
| Fab & Del West Curtainwall | 83
| Fab & Del Windows | 93
| Fab & Del Wood Doors & Hardware | 30
| Install Windows | 25
| Install Wood Doors / Hardware | 10
| Install Plastic in Windows - 2nd flr | 5
| Install Curtainwall | 10
| Densglass Entrance | 8
| Install Alum Exterior Entrance Doors | 5
| Install Alum DFH -East | 5
| Install Glass Handrail - 2nd flr | 3
090 | Finishes
| Fab & Del Exterior Studs / Dens | 10
| Fab & Del Drywall | 14
| Fab & Del Painting | 94
| Fab & Del Act Ceil Grid | 96
| Fab & Del Vynil Tile, FEC | 30
| Fab & Del Custom Carpet 1st flr | 84
| Install Exterior Studs/ Sheath | 20
| Install Interior Studs and Frames | 25
| Sheetrock Chases | 8
| Build Elevator Shaft | 15
| Insulate/Hang Drywall | 15
| Install & Densdeck - Attic | 15
| Fnish Drywal | 20
| Prime Paint | 13
| Install Ceiling Grid | 10
| Install Sheetrock & Tape Ceiling | 20
| Install Flooring - 2nd flr | 10
| Frame Entrance | 6
| Ceramic Tile Toilet | 3
| Install Slate Flooring - 1st flr | 5
| Flood Ceiling Tile | 9
| Final Paint | 8
| Complete Attic Insulation | 5
100 | Specialties
| Fab & Del Folding Partition Wall & Rail | 150
| Install Folding Partition Support Wall & Rail | 3
| Fab & Del Signage | 60
| Install Signage in Building | 4
140 | Elevator
| Fab & Del Elevator | 131
| Install Elevator | 15
| Elevator Machine Room Rough- 14A - Basement | 15
150 | Mechanical
| MEP Slab on Grade Prep | 15
| MEP Second Floor Slab On Deck Prep | 4
| Install Roof Drains & Vents - Roof | 3
| Fab & Del Duct | 27
| Overhead Ductwork | 25
| Overhead Plumbing, Sprinkler, Heat Pipe | 25
| Plumbing & Mechanical Rough-in Mech / Elect room | 77
| Plumbing in-Wall Rough | 9
| Heat Rough-in Mech / Elect room | 68
| Mechanical & Plumbing Rough-in Attic | 29
| Sprinkler Rough-in Mech/Elect Rms | 104
| Mechanical & Plumbing Finish | 7
| Install Sprinkler Heads | 10
160 | Electrical
| Electric Relocation Work | 8
| Overhead Electric | 15
| Electrical In-Wall | 15
| Control In-Wall | 10
| Fire Alarm | 15
| Electrical Rough-in - Attic | 10
| Electrical Finish | 12
| Del Main Transformer | 23
| R.I Lights Entrance | 3
| Electrical Coordination | 14