## Template
Task Code | WBS | Task Name | Target Duration
Activity ID | CSI Code | Activity Name | Original Duration(d)
10 |  | START SCHEDULE | 1
1000 | 16050 | Electric Relocation Work- Phase 1-16A | 3
1020 | 16050 | Shutdown #1- 16A | 1
1030 | 16050 | Electric Relocation Work- Phase 2-16A | 5
1100 | 02200 | Erect Fence/Prep Site/Erosion Control- 02A | 4
1060 | 16050 | Shutdown #2- 16A | 1
1070 | 16050 | Energize New HV Loop- 16A | 1
1050 | 03100 | Place Concrete for New Ductbank- 16A | 2
1130 | 03100 | Form/Place/Strip Balance of Footings- 02A | 3
1110 | 02200 | Exc. Bsmt/Prep for Found Footings- 02A | 5
1080 | 02050 | Demo Ductbank/MH- 02A | 2
1090 | 02200 | Backfill/Restore Grade- 02A | 1
1210 | 05100 | Steel Shops Submitted | 1
1220 | 05100 | Steel Shops Approved/Returned | 10
1115 | 05520 | Deliver Anchor Bolts/Embeds- 05A | 1
1126 | 02450 | Prep for Balance of Footings- 02A | 3
1122 | 02600 | Install Sewer Line- 02A | 15
1120 | 03100 | Form/Place/Strip Basement Footings- 03A | 3
1150 | 03100 | Form/Place/Strip Basement Walls- 03A | 4
1153 | 07100 | Partially Dampproof & Insulate Foundation | 4
1160 | 03100 | Forms/Place/Strip Balance of Walls- 03A | 8
1225 | 05100 | Fabricate Steel | 41
1124 | 02600 | Install Water Line/Tap- 02A | 15
5012 | 05300 | Sub Shp Dwgs | 10
5402 | 14200 | Sub SD Elevator | 10
1170 | 15700 | Install U/G Ductwork- 15B | 5
1175 | 02200 | Backfill Int. Fnd. Walls & U/G Duct- 02A | 2
5042 | 07500 | Sub Roofing EPDM Shp Dwgs | 10
5052 | 07300 | Sub Roofing Slat Shp Dwgs | 10
5062 | 08500 | Sub Windows Shp Dwsg | 10
5072 | 08900 | Sub Curtain Shp Dwgs | 10
5370 | 08050 | Arch Compl Door Schedule | 10
5082 | 09250 | Sub Drywall Shp Dwgs | 25
5092 | 06100 | Sub Struct Studs / Dens Shp Dwgs (Dens sub) | 11
5112 | 10651 | Sub Folding Part Shp Dwgs | 11
5102 | 09550 | Sub Act Ceil Shp Dwgs | 41
5122 | 09100 | Sub FEC Shp Dwgs | 41
5212 | 06400 | Prep Millwork Bid Pkg | 6
5022 | 05520 | Sub Stair Shp Dwgs | 15
5412 | 15700 | Mechanical Coordination Duct mech Ppg/Pimg | 10
5000 | 04200 | Fab & Del Brick | 55
5014 | 05300 | A/E Review Deck Shp Dwgs | 5
1155 | 02200 | Partially Backfill Basement Walls- 02A | 1
1177 | 02200 | Excavate for U/G Plumbing- 02A | 2
1230 | 05520 | Survey Anchor Bolts | 2
5016 | 05300 | Fab & Del Deck | 2
5372 | 08100 | Prep Frames / Hardware Bid Pkg | 10
1180 | 15400 | Install U/G Plumbing- 15B | 10
5064 | 08500 | A/E Review WindowsShp Dwgs | 10
5074 | 08900 | A/E Curtainwall Shp Dwgs | 10
5044 | 07500 | A/E Review EPDM Shp Dwgs - rejected | 15
5054 | 07300 | A/E Review Slate Shp Dwgs | 10
1196 | 07100 | Install Dampproofing/Insulation- 03A | 2
5214 | 06400 | Bid Period Millwork | 15
5374 | 08100 | Bid Drs / frames / Hardware | 15
5001 | 04200 | A/E Review Precast SD | 10
1198 | 02200 | Backfill/Rgh Grade Foundation & Site- 02A | 3
1183 | 03302 | Prep/Place Basement SOG- 03A | 4
5024 | 05520 | A/E Review Stair Shp Dwgs | 10
1204 | 02200 | Prep Site for Steel | 6
1202 |  | President's Inauguration/Commencement | 1
5414 | 15300 | Sprinkler Coord | 14
5416 | 16050 | Electrical Coord | 14
5076 | 08900 | Fab & Del West Curtainwall | 83
5066 | 08500 | Fab & Del Windows | 93
1185 | 03302 | Prep/Place Main SOG- 03A | 5
5084 | 09250 | A/E review Drywall Shp Dwgs | 10
1240 | 05100 | Steel Delivery | 1
1351 | 15700 | Set AHU/Mechanical Room Equipment- 15B | 5
1260 | 05100 | Erect Basement Steel | 3
5342 | 12600 | Prep Aud Seating Bid Pkg | 12
5132 | 09600 | Prep Flooring Bid Pkg | 15
5182 | 09900 | Prep Painting Bid Bkg | 15
5026 | 05520 | Fab & Del Stairs 1 & 2 MAIN STAIRS | 38
5311 | 10400 | Owner Clarify Signage Bid Pkg | 53
1270 | 05100 | Erect First Floor Steel | 5
1275 | 05100 | Erect Second Floor Steel | 5
5376 | 08100 | Eval & Recom Award Drs/Frames/Hardware | 5
5216 | 06400 | Eval & Recom Award Millwork | 8
1277 | 05100 | Erect Attic Steel | 3
5045 | 07500 | Resubmit EPDM Shp Dwgs | 5
5056 | 07300 | Fab & Del Slate Roofing | 30
1280 | 05100 | Erect Roof Steel | 10
1255 |  | WPI Reunion Weekend | 1
1290 | 05300 | Install Roof Decking | 5
5378 | 08100 | Owner App Award Drs/Frames/Hardware | 2
5384 | 08100 | Award Aud Drs/ Frames/Hardware | 1
1340 | 02200 | Backfill/Prep Landing-02A | 5
1318 | 05100 | Install Precast Supports / Adjust | 9
5096 | 05500 | Fab & Del Exterior Studs / Dens | 10
5386 | 08100 | Sub SD Drs/Frames/Hardware | 24
1380 | 15500 | Mechanical Rough-in-15B-Mech RM | 77
1295 | 05300 | Install First Floor Deck/Studs | 1
1297 | 05300 | Install Second Floor Deck/Studs | 1
1300 | 05300 | Install Attic Deck | 4
1298 | 15700 | MEP Slab Prep First Floor | 2
5222 | 06400 | Owner App Award Millwork | 2
6094 | 06100 | A/E Structural Studs / DensShp Dwgs | 10
5114 | 10651 | A/E Folding Part Shp Dwgs | 10
1299 | 03300 | Prep/pour First Floor SOD | 5
5047 | 07500 | A/E Review EPDM Shp Dwgs | 5
5002 | 03400 | Fab & Del Precast | 25
5344 | 12600 | Bid Period Aud Seating | 17
2190 | 06100 | Stock Insulation, Densdeck & Plywood- 09A - Attic | 1
5224 | 06400 | Award Millwork | 1
1302 | 15700 | MEP Second Floor SOD Prep | 2
5086 | 09250 | Fab & Del Drywall | 14
5104 | 09510 | A/E Act Ceil Shp Dwgs | 10
5134 | 09600 | Bid Period Flooring | 18
5184 | 09900 | Bid Period Painting | 22
5032 | 06400 | Sub Millwork Shp Dwgs | 15
1304 | 03300 | Prep/Pour Second Floor SOD | 2
5420 | 15950 | MEP Coordination Signoff | 5
2490 | 06100 | Inst 1st & 2nd Flr/Gable Ext. Studs/ Sheath -East | 14
5046 | 07500 | Fab & Del EPDM Roofing | 40
1390 | 15700 | Heat Rough-in- 15B - Mech / Elect room | 68
1400 | 15400 | Plumbing Rough-in- 15B - Mech / Elect room | 66
5422 | 15500 | Fab & Del Duct - 2nd flr | 27
5116 | 05520 | Fab & Del Folding Part Rail | 150
5117 | 05520 | Fab & Del Folding Part Wall | 10
1577 | 09100 | Layout 1st floor and Top Track | 2
5404 | 14200 | A/E Review Sd Elevator | 10
3090 | 07700 | Install Roof Drains & Vents - Roof | 3
5027 | 05520 | fab & Del Basement Stair | 25
5392 | 08100 | Fab & Del Drs/Frames/Hardware | 15
2520 | 04200 | Install 1st & 2nd Floor Brick & Precast East | 27
5418 | 15950 | A/E review MEP Coordination (for record) | 5
2900 | 06100 | Install 1st & 2nd Floor Studs & Sheath - South | 8
2600 | 06100 | Install 1st & 2nd Floor Studs & Sheath - North | 8
5105 | 09550 | Re-Sub Act Ceil Shp Dwgs | 10
5388 | 08100 | A/E Review Sd Drs / Frames / Hardware | 10
1445 | 16300 | Deliver/Install Switchgear- 16A Electric Rms | 1
5406 | 14200 | Fab & Del Elevator | 131
5186 | 09900 | Eval & Recom Award Painting | 5
5346 | 12600 | Eval & Recom Aud Seating | 5
1835 | 15400 | Overhead Heat Pipe - 2nd flr | 10
1580 | 15500 | Overhead Ductwork - 1st flr | 15
1590 | 15400 | Overhead Heat Pipe - 1st flr | 16
5136 | 09050 | Eval Award | 5
1860 | 06100 | Install Interior Studs and Frames - 2nd flr | 10
1885 | 15400 | Plumbing in-Wall Rough - 2nd flr | 4
2546 | 04200 | Install Gable-End Brick & Precast - East (Br dne) | 9
2700 | 06100 | Inst 1st & 2nd floor/Gable Studs & Sheath - West | 9
2770 | 04200 | Install Gable-End Brick & Precast - West | 17
1375 | 06100 | Install Stud Walls/Door Frames- 09A - Basement | 3
2715 | 16050 | Electric Shutdown Switchgear | 2
1630 | 06100 | Install Interior Stud Walls/Door Frames - 1st flr | 8
1855 | 15300 | Overhead Sprinkler - 2nd flr | 10
2720 | 04200 | Install 1st & 2nd Floor Brick & Precast West | 15
3100 | 07600 | Install Roof Sheathing - East - Roof | 3
1503 | 05520 | Install Stairs - basement | 18
6000 | 05520 | Submit Sketch Ladder & Handrail - 05A - Attic | 3
6010 | 07300 | Fab & Del Slate Infills North | 124
3110 | 07600 | Install Rood Sheathing - North | 3
2610 | 04200 | Install 1st & 2nd Floor Brick & Precast - North | 17
5192 | 09900 | Owner App award Painting | 2
5348 | 12600 | Owner App Award Aud Sealing | 2
5107 | 09550 | A/E Review Re-Sub Act Ceil Shp Dwgs | 10
1840 | 15400 | Overhead Plumbing - 2nd flr | 3
1600 | 15400 | Overhead Plumbing - 1st flr | 5
1924 | 08500 | Install Plastic in Windows - 2nd flr | 5
3130 | 07600 | Installation of Sheathing - South | 3
5194 | 09900 | Award Painting | 1
5354 | 12600 | Award Aud Seating | 1
5124 | 09100 | A/E FEC Shp Dwgs | 10
1636 | 15400 | Plumbing In-Wall Rough - 1st flr | 5
1620 | 15300 | Overhead Sprinkler - 1st flr | 10
1360 | 05520 | Install Stairs/Areaway Grates-05A basement | 12
1850 | 16050 | Overhead Electric - 2nd flr | 5
1663 | 15700 | Insulate Duct & Piping - 1st flr | 5
2910 | 04200 | Install 1st & 2nd Floor Brick & Precast - South | 8
1610 | 16050 | Overhead Electric - 1st flr | 10
1661 | 09100 | Frame Chases - 1st flr | 2
1921 | 09100 | Frame Chases - 2nd flr | 2
2005 | 05520 | Sub SD Ladder & Handrail - 05A - Attic | 107
5142 | 09600 | Owner App award Flooring | 2
5144 | 09600 | Award Flooring | 1
5196 | 09900 | Sub SD Painting | 10
5146 | 09680 | Sub SD Vct | 10
5156 | 09680 | Sub SD Carpet | 10
5166 | 09300 | Sub SD Slate | 10
1890 | 16100 | Electrical In-Wall - 2nd flr | 10
1895 | 16800 | Fire Alarm In-Wall - 2nd flr | 5
1900 | 16300 | Control In-Wall - 2nd flr | 5
1920 | 15700 | Insulate Duct & Piping - 2nd floor | 5
2270 | 15700 | Mechanical Rough-in-14A - Attic | 19
3180 | 07700 | Install EPDM - Pit & Balcony | 5
5034 | 06400 | A/E Review Millwork Shp Dwgs | 10
1410 | 15300 | Sprinkler Rough-in- 15B - Mech/Elect Rms | 104
1905 | 09100 | Build Elevator Shaft - 2nd flr | 5
1465 | 10200 | Install Areaway Louvers- North | 2
3140 | 07300 | Install Slate Shingles- North | 5
5356 | 12600 | Sub SD Aud Seating | 10
1450 | 09100 | Build Elevator Shaftwall- 09A - Basement | 3
1285 | 05520 | Install 1st Floor Stairs & Rails | 5
1640 | 16100 | Electric In-Wall Rough - 1st flr | 5
1922 | 09250 | Sheetrock Chases - 2nd flr | 5
5033 | 06050 | Select Wood Veneer Leed Certification | 5
5198 | 09900 | A/E Review Sd Painting | 10
2291 | 16300 | Del Main Transformer | 23
1645 | 16300 | Control In -Wall Rough - 1st flr | 5
1647 | 16800 | Fire Alarm In-Wall Rough - 1st flr | 5
5106 | 09550 | Fab & Del Act Ceil Grid | 96
5110 | 09550 | Fab & Del Act Ceil Tile | 96
1664 | 09250 | Sheetrock Chases - 1 st flr | 5
2755 | 08900 | Install Partial Curtainwall- West | 7
3190 | 07200 | Temp Dry In Full Roof | 0
1910 | 15950 | MEP Inspections - 2nd flr | 1
1305 | 05520 | Install 2nd Floor Stairs & Rails | 5
5148 | 09680 | A/E Review Sd Vct | 10
6158 | 09680 | A/E Review Sd Carpet | 10
5168 | 09300 | A/E Review Sd Slate | 10
5202 | 09900 | Fab & Del Painting | 84
5126 | 09100 | Fab & Del FEC (Avail) | 30
1660 | 15950 | MEP Inspections - 1st flr | 1
1650 | 09100 | Build Elevator Shaftwall - 1st fl | 7
5358 | 12600 | A/E Review Sd Aud Seating | 10
1925 | 09250 | Insulate/Hang Drywall - 2nd flr | 5
3150 | 07300 | Install Slate shingles- North | 5
2280 | 15400 | Plumbing Rough-in - Attic | 10
2290 | 16050 | Electrical Rough-in - Attic | 10
2550 | 08500 | Install Windows - East | 15
3170 | 07300 | Install Slate Shingles- South | 5
5163 | 09680 | Fab & Del Custom Carpet 1st flr | 84
5152 | 09680 | Fab & Del Vct (Avail) | 30
5162 | 09680 | Fab & Del Carpet | 30
3160 | 07300 | Install Slate Shingles-West | 5
3248 | 03050 | Site Concrete- Mock-up Approved | 3
2780 | 08500 | Install Windows - West | 10
1670 | 09250 | Insulate/Hang Drywall - 1st flr | 5
2300 | 09100 | Install & Densdeck - Attic | 15
2950 | 08500 | Install Windows - South | 5
1350 | 03050 | Form/place Stair Landing -03A - Basement | 5
1460 | 14200 | Elevator Machine Room Rough- 14A - Basement | 15
1325 | 05520 | Install Roof Stairs | 2
1440 | 16800 | Electric/Fire Alarm Rough-in- 16A Mech/ Electr | 8
5036 | 06400 | Fab & Del Millwork | 60
2640 | 08500 | Install Windows - North | 5
1930 | 09250 | Finish Drywall - 2nd flr | 10
1480 | 09250 | Insulate/Hang Drywall- 09A - Basement | 3
1892 |  | Owner Pull Telecommunications 2nd flr | 10
1642 |  | Owner Pull Telecommunications 1st flr | 10
2570 | 08100 | Install Alum DFH -East | 5
2790 | 08100 | Complete CW/Install Alum DFH - West | 2
1470 | 15950 | MEP Inspections Mech / Elect Rms | 1
3200 | 02200 | Site Prep- East & North Sides | 5
1490 | 09250 | Finish Drywall- 09A - Basement | 5
3400 | 02200 | Site Prep- West & South Sides | 5
3260 | 03100 | Site Concrete- East & North Sides | 10
5324 | 10400 | Owner Award Signage | 10
2305 | 06100 | Install Plywood - Attic | 5
1680 | 09250 | Finish Drywall - 1st flr | 8
3452 | 02700 | Final Paving | 1
5326 | 10400 | Sub Signage | 10
1940 | 09900 | Prime Paint - 2nd flr | 5
1685 | 09250 | Sheetrock & Tapes Stairs | 10
3805 | 03400 | Precast - West Entrance | 5
1934 | 08200 | Fab & Del Wood Doors & Hardware - 2nd flr | 30
1972 | 10651 | Install Folding Partition Support Pail - 2nd flr | 1
3450 | 03100 | Site Concrete- West & South Sides | 2
3840 | 07400 | Terminate Roofing - West Entrance | 1
1945 | 09500 | Install Ceiling Grid - 2nd flr | 6
1993 | 14200 | Install Elevator | 15
3800 | 03400 | Precast - East Entrance | 5
3810 | 09100 | Frame - West Entrance | 3
2025 | 09500 | Complete Ceil Grid / Tile 2nd Flr 1-05A - Attic | 3
5328 | 10400 | A/E Review Sd Signage | 10
1690 | 09900 | Prime Paint - 1st Flr | 5
1955 | 15300 | Install Sprinkler Heads - 2nd flr | 5
1942 | 09300 | Ceramic Tile Toilet 2nd flr | 3
3845 | 07400 | Terminate Roofing - east Entrance | 1
1634 | 05520 | Install Presentation Room Stair - 1st flr | 5
1800 | 09250 | Install Sheetrock & Tape Ceiling Lobby - 1st flr | 10
1520 | 16050 | Electrical Finish - Basement | 3
1695 | 09500 | Install Ceiling Grid - 1st floor | 5
1980 | 15400 | Plumbing Finish - 2nd flr | 5
1950 | 15700 | Install D's - 2nd Flr | 5
1692 | 09300 | Ceramic Alum Exterior Entrance Doors | 3
2572 | 08100 | Install Alum Exterior Entrance Doors | 5
1985 | 16050 | Electrical Finish - 2nd flr | 5
1700 | 15700 | Install RGD's - 1st flr | 5
1705 | 15300 | Install Sprinkler Heads - 1st flr | 5
1970 | 09600 | Install Flooring - 2nd flr | 10
1960 | 09500 | Flood Ceiling Tile - 2nd flr | 5
5172 | 09300 | Fab & Del Slate to Customs | 0
2015 |  | Remove Wd Ladder from Rm 2nd Flr 1-05A - Attic | 1
1915 | 08800 | Install Glass Handrail - 2nd flr | 3
1995 | 10980 | Install Specialties - 2nd flr | 10
2020 | 05300 | Install Deck @ Attic 2nd Flr 1-05A- Attic | 1
2260 | 05520 | Install Ladder & Handrail -05A- Attic | 5
6002 | 05520 | Fab & Del Ladder & Handrail-05A- Attic | 10
1505 | 05520 | Install Stair Handrails - Basement | 3
1965 | 06200 | Install Millwork - 2nd flr | 5
2650 | 07300 | Install Slate Infills North | 3
1935 | 08200 | Install Wood Doors & Hardware - 2nd flr | 5
1710 | 09500 | Flood Ceiling Tile - 1st flr | 5
1973 | 10651 | Install Folding Partition Wall - 2nd flr | 1
5332 | 10400 | Fab & Del Signage | 60
1805 | 06200 | Install Wood Paneling in Lobby- 1st flr | 7
1722 | 09300 | Install Slate Flooring - 1st flr | 5
2960 | 07300 | Install Slate Infills - South | 5
1686 | 08200 | Install Wood Doors / Hardware - 1st | 5
3825 | 09100 | Frame - East Entrance | 3
1790 | 09700 | Install Fabric Panels - 1st flr | 3
1795 | 06200 | Install Wood Paneling in Lobby- 1st flr | 3
5359 | 12600 | Gilbane Release Aud Seating (Stain Color) | 5
1975 | 09900 | Final Paint - 2nd flr | 5
1716 | 06200 | Install Millwork - 1st flr | 5
1990 | 15900 | Mechanical Finish - 2nd flr | 5
5362 | 12600 | Fab & Del Aud Seating | 0
2010 | 05520 | Install Stair Rails | 29
3815 | 16500 | R.I. Lights - West Entrance | 1
3820 | 08400 | Densglass - West Entrance | 5
3830 | 16500 | R.I. Lights - East Entrance | 1
3835 | 08400 | Densglass - East Entrance | 5
1720 | 09600 | Complete Flooring - 1st flr | 4
1725 | 09900 | Complete Paint - 1st flr | 3
3700 |  | Fire Marshall Inspect Building | 1
3705 |  | test & Balance Building - Bldg | 6
1997 |  | Punchlist - 2nd flr | 3
1740 | 15900 | Mechanical Finish - 1st flr | 2
1807 | 12600 | Install Presentation Room Seating - 1st flr | 2
1730 | 16050 | Electrical Finish - 1st flr | 3
1727 | 10400 | Install Signage in Building | 4
1750 | 12400 | Install Mecxho Shades - 1st flr | 5
1815 | 01046 | Final Clean - 1st flr | 5
3710 |  | Commissioning Building | 6
3722 |  | Flush Building | 10
2000 | 01046 | Final Cleaning - 2nd flr | 5
3715 |  | Substantial Completion C of O | 5
3860 | 07400 | Ballast Roofing - East Entrance | 1
2013 | 09500 | Complete Attic Insulation | 6
2011 | 12500 | Owner Furniture | 10
3720 |  | WPI Move - in | 38
3600 | 03700 | Place Exterior West Slab | 3
1830 | 15500 | Overhead Duct 2nd flr | 10
1833 | 15700 | Fab & Del Valves Heat Pipe - 2nd flr | 4
3120 | 07600 | Install Roof Sheathing - West | 12
5173 | 09300 | Slate Clear Customs & Deliver | 5
2012 | 06400 | Furnish & Install Plam Top | 5
3821 | 09200 | Plaster - Both Entrance | 5
3650 | 02900 | Landscaping & Brick Paving | 20
2735 |  | WPI Occupy Building | 0
1811 |  | Building Dedication | 0

## USERDATA
user_data
UserSettings Do Not Edit
DurationQtyType=QT_Day ShowAsPercentage=0 SmallScaleQtyType=QT_Hour DateFormat=dd'-'mmm'-'yy CurrencyFormat=Dollar